## Timelines
Timescales are indicative only, they are likely to change due to the timeframes laid out in the Pharmacy Regulations.
Number 13 onwards was paused between December 2022 and July 2023 in line with local policy. Pre Application Meetings recommenced from August 2023.
Details correct at 01/07/2024
|  |  | 2022 | [10 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Number | Date Expression of Interest Recieved | Application Details | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | 2018-03-18 | Granton, Edinburgh | 2022 Feb: Joint Consultation; 2022 Jul: Produce CAR / Application Submitted; 2022 Dec: Hearing; 2023 Mar: NAP - Appeal Upheld - Remitted back to the PPC for reconsideration; 2024 Apr: PPC Decision; 2024 Jun: Appeal Received - with NAP
2 | 2018-04-26 | Burdiehouse, Edinburgh | 2022 Mar: Joint Consultation; 2022 Aug: Produce CAR / Application Submitted; 2023 Jan: Hearing; 2023 Apr: The Health Board has been instructed to consider the application afresh; 2024 Jan: Hearing; 2024 Jun: Appeal Received - with NAP
3 | 2019-11-01 | Linlithgow, West Lothian | 2022 May: Joint Consultation; 2022 Oct: Joint Consultation; 2023 Mar: Produce CAR / Application Submitted; 2023 Aug: Hearing; 2023 Oct: NAP - Appeal Upheld - Remitted back to the PPC for reconsideration; 2024 Jun: PPC Decision
4 | 2020-08-03 | Gilmerton, Edinburgh | 2022 Jul: Joint Consultation; 2022 Dec: Produce CAR / Application Submitted; 2023 May: Hearing
5 | 2021-02-18 | Pumpherston, West Lothian | 2022 Sep: Joint Consultation; 2023 Feb: Produce CAR / Application Submitted; 2023 Jul: Hearing
6 | 2021-05-24 | Calderwood, West Lothian | 2022 Nov: Joint Consultation; 2023 Apr: Produce CAR / Application Submitted; 2023 Sep: Hearing
7 | 2021-07-12 | Whitecraig, East Lothian | 2024 Mar: Joint Consultation; 2024 Aug: Produce CAR / Application Submitted; 2025 Jan: Hearing
8 | 2021-08-24 | Newcraighall, Edinburgh | 2024 Apr: Joint Consultation; 2024 Sept: Produce CAR / Application Submitted; 2025 Feb: Hearing
9 | 2021-12-19 | Rosewell, Midlothian | 2024 Jun: Joint Consultation; 2024 Nov: Produce CAR / Application Submitted; 2025 Apr: Hearing
10 | 2021-12-20 | West Town, Edinburgh | 2024 Jul: Joint Consultation; 2024 Dec: Produce CAR / Application Submitted; 2025 May: Hearing
11 | 2022-01-21 | Blindwells, East Lothian | 2024 Aug: Joint Consultation; 2025 Jan: Produce CAR / Application Submitted; 2025 Jun: Hearing
12 | 2022-03-09 | Dechmont, West Lothian | 2024 Sept: Joint Consultation; 2025 Feb: Produce CAR / Application Submitted; 2025 Jul: Hearing
13 | 2022-04-06 | Redhaughs Village, Gogar | 2024 Oct: Joint Consultation; 2025 Mar: Produce CAR / Application Submitted; 2025 Aug: Hearing
14 | 2022-04-19 | Pencaitland, East Lothian | 2024 Nov: Joint Consultation; 2025 Apr: Produce CAR / Application Submitted; 2025 Sept: Hearing
15 | 2022-04-29 | West Craigs, Edinburgh | 2024 Dec: Joint Consultation; 2025 May: Produce CAR / Application Submitted; 2025 Oct: Hearing
16 | 2022-06-30 | Shawfair, Midlothian | 2025 Jan: Joint Consultation; 2025 Jun: Produce CAR / Application Submitted; 2025 Nov: Hearing
17 | 2022-07-19 | Southdale, near Armadale | 2025 Feb: Joint Consultation; 2025 Jul: Produce CAR / Application Submitted; 2025 Dec: Hearing
18 | 2022-07-20 | Musselburgh, East Lothian | 2025 Mar: Joint Consultation; 2025 Aug: Produce CAR / Application Submitted; 2026 Jan: Hearing
19 | 2022-07-25 | Mayfield, Midlothian | 2025 Apr: Joint Consultation; 2025 Sept: Produce CAR / Application Submitted; 2026 Feb: Hearing
20 | 2022-07-25 | Newtongrange, Midlothian | 2025 May: Joint Consultation; 2025 Oct: Produce CAR / Application Submitted; 2026 Mar: Hearing
21 | 2022-08-03 | Aberlady, East Lothian | 2025 Jun: Joint Consultation; 2025 Nov: Produce CAR / Application Submitted; 2026 Apr: Hearing
22 | 2022-08-11 | Bilston, Midlothian | 2025 Jul: Joint Consultation; 2025 Dec: Produce CAR / Application Submitted; 2026 May: Hearing
23 | 2022-08-27 | Murieston, Livingston | 2025 Aug: Joint Consultation; 2026 Jan: Produce CAR / Application Submitted; 2026 Jun: Hearing
24 | 2022-08-30 | Dedridge, Livingston | 2025 Sept: Joint Consultation; 2026 Feb: Produce CAR / Application Submitted; 2026 Jul: Hearing
25 | 2022-09-13 | Woodburn, Midlothian | 2025 Oct: Joint Consultation; 2026 Mar: Produce CAR / Application Submitted; 2026 Aug: Hearing
26 | 2022-11-07 | Leith, Edinburgh | 2025 Nov: Joint Consultation; 2026 Apr: Produce CAR / Application Submitted; 2026 Sept: Hearing
27 | 2022-11-07 | Kirkliston, Edinburgh | 2025 Dec: Joint Consultation; 2026 May: Produce CAR / Application Submitted; 2026 Oct: Hearing
28 | 2022-11-07 | Dalkeith, Midlothian | 2026 Jan: Joint Consultation; 2026 Jun: Produce CAR / Application Submitted; 2026 Nov: Hearing
29 | 2022-12-04 | Macmerry, East Lothian | 2026 Feb: Joint Consultation; 2026 Jul: Produce CAR / Application Submitted; 2026 Dec: Hearing
30 | 2023-01-18 | Gorgie, Edinburgh | 2026 Mar: Joint Consultation; 2026 Aug: Produce CAR / Application Submitted; 2027 Jan: Hearing
31 | 2023-01-18 | Meadowbank, Edinburgh | 2026 Apr: Joint Consultation; 2026 Sept: Produce CAR / Application Submitted; 2027 Feb: Hearing
32 | 2023-01-18 | Straiton | 2026 May: Joint Consultation; 2026 Oct: Produce CAR / Application Submitted; 2027 Mar: Hearing
33 | 2023-01-18 | Broxburn, West Lothian | 2026 Jun: Joint Consultation; 2026 Nov: Produce CAR / Application Submitted; 2027 Apr: Hearing
34 | 2023-02-07 | Newbridge and Ratho Station | 2026 Jul: Joint Consultation; 2026 Dec: Produce CAR / Application Submitted; 2027 May: Hearing
35 | 2023-02-13 | Dunbar, East Lothian | 2026 Aug: Joint Consultation; 2027 Jan: Produce CAR / Application Submitted; 2027 Jun: Hearing
36 | 2023-02-13 | Currie, Edinburgh | 2026 Sept: Joint Consultation; 2027 Feb: Produce CAR / Application Submitted; 2027 Jul: Hearing
37 | 2023-02-13 | Sighthill, Edinburgh | 2026 Oct: Joint Consultation; 2027 Mar: Produce CAR / Application Submitted; 2027 Aug: Hearing
38 | 2023-02-13 | Bruntsfield, Edinburgh | 2026 Nov: Joint Consultation; 2027 Apr: Produce CAR / Application Submitted; 2027 Sept: Hearing
39 | 2023-02-13 | Westfield, Edinburgh | 2026 Dec: Joint Consultation; 2027 May: Produce CAR / Application Submitted; 2027 Oct: Hearing
40 | 2023-02-13 | Murrayfield, Edinburgh | 2027 Jan: Joint Consultation; 2027 Jun: Produce CAR / Application Submitted; 2027 Nov: Hearing
41 | 2023-02-13 | East Craigs, Edinburgh | 2027 Feb: Joint Consultation; 2027 Jul: Produce CAR / Application Submitted; 2027 Dec: Hearing
42 | 2023-02-13 | Stockbridge, Edinburgh | 2027 Mar: Joint Consultation; 2027 Aug: Produce CAR / Application Submitted; 2028 Jan: Hearing
43 | 2023-02-13 | Gorebridge, Midlothian | 2027 Apr: Joint Consultation; 2027 Sept: Produce CAR / Application Submitted; 2028 Feb: Hearing
44 | 2023-02-13 | Bonnyrigg, Midlothian | 2027 May: Joint Consultation; 2027 Oct: Produce CAR / Application Submitted; 2028 Mar: Hearing
45 | 2023-02-13 | Loanhead, Midlothian | 2027 Jun: Joint Consultation; 2027 Nov: Produce CAR / Application Submitted; 2028 Apr: Hearing
46 | 2023-02-13 | Howden, Livingston | 2027 Jul: Joint Consultation; 2027 Dec: Produce CAR / Application Submitted; 2028 May: Hearing
47 | 2023-05-25 | Ormiston, East Lothian | 2027 Aug: Joint Consultation; 2028 Jan: Produce CAR / Application Submitted; 2028 Jun: Hearing
48 | 2023-06-10 | Eskbank, Midlothian | 2027 Sept: Joint Consultation; 2028 Feb: Produce CAR / Application Submitted; 2028 Jul: Hearing
49 | 2023-10-05 | Tranent, East Lothian | 2027 Oct: Joint Consultation; 2028 Mar: Produce CAR / Application Submitted; 2028 Aug: Hearing
50 | 2023-12-22 | Muirhouse, Edinburgh | 2027 Nov: Joint Consultation; 2028 Apr: Produce CAR / Application Submitted; 2028 Sept: Hearing
51 | 2023-12-28 | Wester Hailes, Edinburgh | 2027 Dec: Joint Consultation; 2028 May: Produce CAR / Application Submitted; 2028 Oct: Hearing
52 | 2024-01-22 | Longridge, West Lothian | 2028 Jan: Joint Consultation; 2028 Jun: Produce CAR / Application Submitted; 2028 Nov: Hearing
53 | 2024-02-12 | Elements, Edinburgh | 2028 Feb: Joint Consultation; 2028 Jul: Produce CAR / Application Submitted; 2028 Dec: Hearing
54 | 2024-04-11 | Whitburn, Heartlands, West Lothian | 2028 Mar: Joint Consultation; 2028 Aug: Produce CAR / Application Submitted; 2029 Jan: Hearing
55 | 2024-04-29 | Bangour, West Lothian | 2028 Apr: Joint Consultation; 2028 Sept: Produce CAR / Application Submitted; 2029 Feb: Hearing
56 | 2024-05-15 | Haddington, East Lothian | 2028 May: Joint Consultation; 2028 Oct: Produce CAR / Application Submitted; 2029 Mar: Hearing
57 | 2024-05-28 | Bathgate, West Lothian
58 | 2024-06-04 | South Queensferry, Edinburgh | 2028 Jun: Joint Consultation; 2028 Nov: Produce CAR / Application Submitted; 2029 Apr: Hearing
59 | 2024-06-06 | Winchburgh, West Lothian | 2028 Aug: Joint Consultation; 2029 Jan: Produce CAR / Application Submitted; 2029 Jun: Hearing