## Timelines
Timescales are indicative only, they are likely to change due to the timeframes laid out in the Pharmacy Regulations.
Details correct at 01/10/2026
|  |  | 2024 | [5 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030 | [10 empty] | 2031 | [11 empty] | 2032 | [11 empty] | 2033
Number | Date Expression of Interest Recieved | Application Details | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
1 | 2021-12-19 | Rosewell, Midlothian | 2024 Jul: Joint Consultation; 2024 Dec: Produce CAR / Application Submitted; 2025 May: Hearing; 2025 Nov: Appeal Submitted; 2026 Jan: NAP outcome - Board to review application
2 | 2022-08-11 | Bilston, Midlothian | 2026 Dec: Joint Consultation; 2027 May: Produce CAR / Application Submitted; 2027 Oct: Hearing
3 | 2022-08-27 | Murieston, Livingston | 2027 Jan: Joint Consultation; 2027 Jun: Produce CAR / Application Submitted; 2027 Nov: Hearing
4 | 2022-08-30 | Dedridge, Livingston | 2027 Feb: Joint Consultation; 2027 Jul: Produce CAR / Application Submitted; 2027 Dec: Hearing
5 | 2022-09-13 | Woodburn, Midlothian | 2027 Mar: Joint Consultation; 2027 Aug: Produce CAR / Application Submitted; 2028 Jan: Hearing
6 | 2022-11-07 | Leith, Edinburgh | 2027 Apr: Joint Consultation; 2027 Sept: Produce CAR / Application Submitted; 2028 Feb: Hearing
7 | 2022-11-07 | Kirkliston, Edinburgh | 2027 May: Joint Consultation; 2027 Oct: Produce CAR / Application Submitted; 2028 Mar: Hearing
8 | 2022-11-07 | Dalkeith, Midlothian | 2027 Jun: Joint Consultation; 2027 Nov: Produce CAR / Application Submitted; 2028 Apr: Hearing
9 | 2022-12-04 | Macmerry, East Lothian | 2027 Jul: Joint Consultation; 2027 Dec: Produce CAR / Application Submitted; 2028 May: Hearing
10 | 2023-01-18 | Gorgie, Edinburgh | 2027 Aug: Joint Consultation; 2028 Jan: Produce CAR / Application Submitted; 2028 Jun: Hearing
11 | 2023-01-18 | Meadowbank, Edinburgh | 2027 Sept: Joint Consultation; 2028 Feb: Produce CAR / Application Submitted; 2028 Jul: Hearing
12 | 2023-01-18 | Straiton, Midlothian | 2027 Oct: Joint Consultation; 2028 Mar: Produce CAR / Application Submitted; 2028 Aug: Hearing
13 | 2023-01-18 | Broxburn, West Lothian | 2027 Nov: Joint Consultation; 2028 Apr: Produce CAR / Application Submitted; 2028 Sept: Hearing
14 | 2023-02-07 | Newbridge and Ratho Station | 2027 Dec: Joint Consultation; 2028 May: Produce CAR / Application Submitted; 2028 Oct: Hearing
15 | 2023-02-13 | Dunbar, East Lothian | 2028 Jan: Joint Consultation; 2028 Jun: Produce CAR / Application Submitted; 2028 Nov: Hearing
16 | 2023-02-13 | Currie, Edinburgh | 2028 Feb: Joint Consultation; 2028 Jul: Produce CAR / Application Submitted; 2028 Dec: Hearing
17 | 2023-02-13 | Sighthill, Edinburgh | 2028 Mar: Joint Consultation; 2028 Aug: Produce CAR / Application Submitted; 2029 Jan: Hearing
18 | 2023-02-13 | Bruntsfield, Edinburgh | 2028 Apr: Joint Consultation; 2028 Sept: Produce CAR / Application Submitted; 2029 Feb: Hearing
19 | 2023-02-13 | Westfield, Edinburgh | 2028 May: Joint Consultation; 2028 Oct: Produce CAR / Application Submitted; 2029 Mar: Hearing
20 | 2023-02-13 | Murrayfield, Edinburgh | 2028 Jun: Joint Consultation; 2028 Nov: Produce CAR / Application Submitted; 2029 Apr: Hearing
21 | 2023-02-13 | East Craigs, Edinburgh | 2028 Jul: Joint Consultation; 2028 Dec: Produce CAR / Application Submitted; 2029 May: Hearing
22 | 2023-02-13 | Stockbridge, Edinburgh | 2028 Aug: Joint Consultation; 2029 Jan: Produce CAR / Application Submitted; 2029 Jun: Hearing
23 | 2023-02-13 | Gorebridge, Midlothian | 2028 Sept: Joint Consultation; 2029 Feb: Produce CAR / Application Submitted; 2029 Jul: Hearing
24 | 2023-02-13 | Bonnyrigg, Midlothian | 2028 Oct: Joint Consultation; 2029 Mar: Produce CAR / Application Submitted; 2029 Aug: Hearing
25 | 2023-02-13 | Loanhead, Midlothian | 2028 Nov: Joint Consultation; 2029 Apr: Produce CAR / Application Submitted; 2029 Sept: Hearing
26 | 2023-02-13 | Howden, Livingston | 2028 Dec: Joint Consultation; 2029 May: Produce CAR / Application Submitted; 2029 Oct: Hearing
27 | 2023-05-25 | Ormiston, East Lothian | 2029 Jan: Joint Consultation; 2029 Jun: Produce CAR / Application Submitted; 2029 Nov: Hearing
28 | 2023-06-10 | Eskbank, Midlothian | 2029 Feb: Joint Consultation; 2029 Jul: Produce CAR / Application Submitted; 2029 Dec: Hearing
29 | 2023-10-05 | Tranent, East Lothian | 2029 Mar: Joint Consultation; 2029 Aug: Produce CAR / Application Submitted; 2030 Jan: Hearing
30 | 2023-12-22 | Muirhouse, Edinburgh | 2029 Apr: Joint Consultation; 2029 Sept: Produce CAR / Application Submitted; 2030 Feb: Hearing
31 | 2023-12-28 | Wester Hailes, Edinburgh | 2029 May: Joint Consultation; 2029 Oct: Produce CAR / Application Submitted; 2030 Mar: Hearing
32 | 2024-01-22 | Longridge, West Lothian | 2029 Jun: Joint Consultation; 2029 Nov: Produce CAR / Application Submitted; 2030 Apr: Hearing
33 | 2024-02-12 | Elements, Edinburgh | 2029 Jul: Joint Consultation; 2029 Dec: Produce CAR / Application Submitted; 2030 Jun: Hearing
34 | 2024-04-11 | Whitburn, Heartlands, West Lothian | 2029 Aug: Joint Consultation; 2030 Jan: Produce CAR / Application Submitted; 2030 Jul: Hearing
35 | 2024-04-29 | Bangour, West Lothian | 2029 Sept: Joint Consultation; 2030 Feb: Produce CAR / Application Submitted; 2030 Aug: Hearing
36 | 2024-05-15 | Haddington, East Lothian | 2029 Oct: Joint Consultation; 2030 Mar: Produce CAR / Application Submitted; 2030 Sept: Hearing
37 | 2024-05-28 | Bathgate, West Lothian | 2029 Nov: Joint Consultation; 2030 Apr: Produce CAR / Application Submitted; 2030 Oct: Hearing
38 | 2024-06-04 | South Queensferry, Edinburgh | 2029 Dec: Joint Consultation; 2030 Jun: Produce CAR / Application Submitted; 2030 Nov: Hearing
39 | 2024-06-06 | Winchburgh, West Lothian | 2030 Jan: Joint Consultation; 2030 Jul: Produce CAR / Application Submitted; 2030 Dec: Hearing
40 | 2024-06-19 | Penicuik, Midlothian | 2030 Feb: Joint Consultation; 2030 Aug: Produce CAR / Application Submitted; 2031 Jan: Hearing
41 | 2024-07-05 | Gilmerton, Edinburgh | 2030 Mar: Joint Consultation; 2030 Sept: Produce CAR / Application Submitted; 2031 Feb: Hearing
42 | 2024-07-13 | Wallyford, East Lothian | 2030 Apr: Joint Consultation; 2030 Oct: Produce CAR / Application Submitted; 2031 Mar: Hearing
43 | 2024-08-21 | East Calder, West Lothian | 2030 Jun: Joint Consultation; 2030 Nov: Produce CAR / Application Submitted; 2031 Apr: Hearing
44 | 2024-09-25 | Linlithgow, West Lothian | 2030 Jul: Joint Consultation; 2030 Dec: Produce CAR / Application Submitted; 2031 May: Hearing
45 | 2024-10-07 | Pumpherston, West Lothian | 2030 Aug: Joint Consultation; 2031 Jan: Produce CAR / Application Submitted; 2031 Jun: Hearing
46 | 2024-10-09 | Granton, Edinburgh | 2030 Sept: Joint Consultation; 2031 Feb: Produce CAR / Application Submitted; 2031 Jul: Hearing
47 | 2024-10-15 | West Town, Edinburgh | 2030 Oct: Joint Consultation; 2031 Mar: Produce CAR / Application Submitted; 2031 Aug: Hearing
48 | 2024-10-31 | Newcraighall, Edinburgh | 2030 Nov: Joint Consultation; 2031 Apr: Produce CAR / Application Submitted; 2031 Sept: Hearing
49 | 2024-11-04 | Whitecraig, East Lothian | 2030 Dec: Joint Consultation; 2031 May: Produce CAR / Application Submitted; 2031 Oct: Hearing
50 | 2024-12-16 | Calderwood, West Lothian | 2031 Jan: Joint Consultation; 2031 Jun: Produce CAR / Application Submitted; 2031 Nov: Hearing
51 | 2025-02-21 | Redhaughs Village, Gogar | 2031 Feb: Joint Consultation; 2031 Jul: Produce CAR / Application Submitted; 2031 Dec: Hearing
52 | 2025-03-13 | Gavieside Village, West Lothian | 2031 Mar: Joint Consultation; 2031 Aug: Produce CAR / Application Submitted; 2032 Jan: Hearing
53 | 2025-08-13 | West Craigs, Edinburgh | 2031 Apr: Joint Consultation; 2031 Sept: Produce CAR / Application Submitted; 2032 Feb: Hearing
54 | 2025-09-08 | Millerhill, Midlothian | 2031 May: Joint Consultation; 2031 Oct: Produce CAR / Application Submitted; 2032 Mar: Hearing
55 | 2025-09-18 | Shawfair, Midlothian | 2031 Jun: Joint Consultation; 2031 Nov: Produce CAR / Application Submitted; 2032 Apr: Hearing
56 | 2025-11-27 | Portobello, Edinburgh | 2031 Jul: Joint Consultation; 2031 Dec: Produce CAR / Application Submitted; 2032 May: Hearing
57 | 2025-12-16 | Blindwells, East Lothian | 2031 Aug: Joint Consultation; 2032 Jan: Produce CAR / Application Submitted; 2032 Jun: Hearing
58 | 2025-12-28 | Southdale, near Armadale | 2031 Sept: Joint Consultation; 2032 Feb: Produce CAR / Application Submitted; 2032 Jul: Hearing
59 | 2026-02-18 | Pencaitland, East Lothian | 2031 Oct: Joint Consultation; 2032 Mar: Produce CAR / Application Submitted; 2032 Aug: Hearing
60 | 2026-04-20 | Herriot Watt Uni Campus, Edinburgh | 2031 Nov: Joint Consultation; 2032 Apr: Produce CAR / Application Submitted; 2032 Sept: Hearing
61 | 2026-05-21 | Edmonstone Village, Midlothian | 2031 Dec: Joint Consultation; 2032 May: Produce CAR / Application Submitted; 2032 Oct: Hearing
62 | 2026-06-16 | Mayfield, Midlothian | 2032 Jan: Joint Consultation; 2032 Jun: Produce CAR / Application Submitted; 2032 Nov: Hearing
63 | 2026-06-16 | Lingerwood, Midlothian | 2032 Feb: Joint Consultation; 2032 Jul: Produce CAR / Application Submitted; 2032 Dec: Hearing
64 | 2026-07-27 | Newtongrange, Midlothian | 2032 Mar: Joint Consultation; 2032 Aug: Produce CAR / Application Submitted; 2033 Jan: Hearing
65 | 2026-08-11 | Dalmeny, West Lothian | 2032 Apr: Joint Consultation; 2032 Sept: Produce CAR / Application Submitted; 2033 Feb: Hearing
66 | 2026-08-11 | Wilkieston, West Lothian | 2032 May: Joint Consultation; 2032 Oct: Produce CAR / Application Submitted; 2033 Mar: Hearing
67 | 2026-08-21 | Aberlady, East Lothian | 2032 Jun: Joint Consultation; 2032 Nov: Produce CAR / Application Submitted; 2033 Apr: Hearing